## TestCase BanglaShoppers
Product Name |  | Bangla Shoppers | TC Start Date | 2024-01-01 | TC Execution Start Date | 2024-03-01 |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 2024-02-01 | TC Execution End Date | 2024-04-01 |  |  |  |  | PASS | 40
Epic |  |  | Test Case Developed By | Nuriad Islam | Browser (tested) | Yes |  |  |  |  | FAIL | 11
Developer Name (TL) |  |  | Test Case Reviewed By | Priya Tahsina | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 51
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Check red asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checkbox beside 'Sign Up for Newsletter' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Check checkbox beside 'Sign Up for Newsletter' |  |  | Passed
8 |  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present | No "Remember me" found | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' | "Remember me" error |  | Failed
9 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3.Keep mandatory fields blank |  |  | Passed
10 |  |  |  | Checking firstname and lastname field is case insensitive | Should accept the provided input | Found as per expectation | AabcD MmnoP | 1. Goto the URL https://www.banglashoppers.com/ 2. Input AbbCCdd and uuXXggDD in firstname and lastname field |  |  | Passed
11 |  |  |  | Entering blank at first position in firstname and lastname field | Should not accept the provided input | Not found as per expectation | Abdur Rahman | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Input space at first position of firstname and lastname | First blank position error |  | Failed
12 |  |  |  | Entering blank at last position of firstname and lastname field | Should not accept the provided input | Not found as per expectation | Abdur Rahman | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Input space at last position of firstname and lastname | Last blank position error |  | Failed
13 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Keeping blank in each field and checking repeatedly |  |  | Passed
14 |  |  |  | Inputing firstname and lastname with special characters | Should not accept the provided input | Not found as per expectation | @@@@@ &&&&& | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter special characters in firstname and lastname field | Special character error |  | Failed
15 |  |  |  | Inputing firstname and lastname with numbers | Should not accept the provided input | Not found as per expectation | 12345 6789 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter numbers in firstname and lastname field | Numbers error |  | Failed
16 |  |  |  | Inputing firstname and lastname with decimal numbers | Should not accept the provided input | Not found as per expectation | 78.7568.99 87.9878.4 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter decimal numbers in firstname and lastname field | Decimal numbers error |  | Failed
17 |  |  |  | Inputing firstname and lastname with alphanumeric characters | Should accept the provided input | Found as per expectation | Nasir52 Uddin09 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter alphanumeric characters in firstname and lastname field |  |  | Passed
18 |  |  |  | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | Nasir Uddin | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter alphabets in firstname and lastname field |  |  | Passed
19 |  |  |  | Entering comma between alphabets for firstname and lastname | Should not accept the provided input | Not found as per expectation | Na,sir Ud,din | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter comma alphabets in firstname and lastname field | Comma between alphabets error |  | Failed
20 |  |  |  | Entering space between alphabets for firstname and lastname | Should accept the provided input | Found as per expectation | Na sir Ud din | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter space between alphabets in firstname and lastname field |  |  | Passed
21 |  |  |  | Checking newsteller checkbox | Should function successfully | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Select the newsteller checkbox |  |  | Passed
22 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | tnuriad5@gmail.com | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill the email address with already registered email |  |  | Passed
23 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation | thjshhfdsj@hdjkfl | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
24 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | tnuriad5@gmail.com | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill the email address with valid email address format |  |  | Passed
25 |  |  |  | Checking password and confirm field values are masked | Should be masked | Found as per expectation | A1234567 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter password and confirm password |  |  | Passed
26 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation | abcdefgh | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter invalid combinations of characters in password and confirm password |  |  | Passed
27 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation | abcd1234 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter weak password length in password and confirm password |  |  | Passed
28 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter medium password length in password and confirm password |  |  | Passed
29 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | Abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter strong password length in password and confirm password |  |  | Passed
30 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | Password: ABCD1234 Confirm password: abcd1234 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter different values in password and confirm password |  |  | Passed
31 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | Akhh123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter valid credentals in password and confirm password |  |  | Passed
32 |  |  |  | Checking registration with invalid email address | Should not allow user to register and pop an error message | Not found as per expectation | Firstname: Nasir Lastname: Uddin Email: thjshhfdsj@hdjkfl.com Password:abcd123@ Confirm Password:abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Register' | Invalid email address error |  | Failed
33 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | Firstname: Nasir Lastname: Ahmed Email: nasir123@gmail.com Password:abcd123@ Confirm Password:abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Register' |  |  | Passed
34 |  |  |  | Checking confirmation mail sent to the registered email | Sent successfully | Found as per expectation | Firstname: Nasir Lastname: Ahmed Email: nasir123@gmail.com Password:abcd123@ Confirm Password:abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click ' Register' 5. Check mail and confirm account |  |  | Passed
35 |  |  |  | Checking 'Sign in with Facebook' | Should allow user to register | Not found as per expectation | Click on 'Sign in with Facebook' | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Click on 'login with Facebook' | Log in with facebook error |  | Failed
36 |  |  |  | Checking 'Sign in with Google' | Should allow user to register | Found as per expectation | Click on 'Sign in with Google' | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Click on 'login with Google' |  |  | Passed
37 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | Nasir69 | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
38 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
39 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter enter in every field |  |  | Passed
40 |  | Functionality Testing | Sign In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3. Keep both the fields blank |  |  | Passed
41 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | Abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3. Input values in password field and check if it is masked |  |  | Passed
42 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | asdfg@nndj.com ABCD123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3. Input invalid credentials in email and password field |  |  | Passed
43 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email: nasir123@gmail.com Password: abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3. Input valid credentials in email and password field |  |  | Passed
44 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Passed
45 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Not found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' multiple times | Selecting "Forgot Password" multiple times error |  | Failed
46 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
47 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' |  |  | Passed
48 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | Email: tnuriad5@gmail.com Password: abcd1234@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  |  | Passed
49 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Not found as per expectation | Email: tnuriad5@gmail.com Password: abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password | Inputing Old password on"set a new password" error |  | Failed
50 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | Email: tnuriad5@gmail.com Password: abcd123@ | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on login |  |  | Passed
51 |  |  |  | Checking if the link gets dissolved setting a new password | Link should get dissolved | Found as per expectation | N/A | 1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on 'Create New password' |  |  | Passed
|  |  | Improvement Scopes | 'Remember Me' checkbox should be selected according to user
A maximum length of the password should be defined
"Show password" should be enable in "register" & "log in"
Captcha should be added for security.

## Bug Report
Bug Reporting
# SL 01
Issue: Checkbox beside 'Remember Me'
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me'
Env: Production.
Module: Register
Screenshot: "Remember me" error
Expected: Remember me & Checkbox should be present.
Responsible QA: Nuriad Islam
Bug Reporting
# SL 02
Issue: Entering blank at first position in firstname and lastname field
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Input space at first position of firstname and lastname
Env: Production.
Module: Register
Screenshot: First blank position error
Expected: Should not accept the provided input
Responsible QA: Nuriad Islam
Bug Reporting
# SL 03
Issue: Entering blank at last position of firstname and lastname field
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Input space at last position of firstname and lastname
Env: Production.
Module: Register
Screenshot: Last blank position error
Expected: Should not accept the provided input
Responsible QA: Nuriad Islam
Bug Reporting
# SL 04
Issue: Inputing firstname and lastname with special characters
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter special characters in firstname and lastname field
Env: Production.
Module: Register
Screenshot: Special character error
Expected: Should not accept the provided input
Responsible QA: Nuriad Islam
Bug Reporting
# SL 05
Issue: Inputing firstname and lastname with numbers
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter numbers in firstname and lastname field
Env: Production.
Module: Register
Screenshot: Numbers error
Expected: Should not accept the provided input
Responsible QA: Nuriad Islam
Bug Reporting
# SL 06
Issue: Inputing firstname and lastname with decimal numbers
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter decimal numbers in firstname and lastname field
Env: Production.
Module: Register
Screenshot: Decimal numbers error
Expected: Should not accept the provided input
Responsible QA: Nuriad Islam
Bug Reporting
# SL 07
Issue: EEntering comma between alphabets for firstname and lastname
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Enter comma alphabets in firstname and lastname field
Env: Production.
Module: Register
Screenshot: Comma between alphabets error
Expected: Should not accept the provided input
Responsible QA: Nuriad Islam
Bug Reporting
# SL 08
Issue: Checking registration with invalid email address
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Register'
Env: Production.
Module: Register
Screenshot: Invalid email address error
Expected: Should not allow user to register and pop an error message
Responsible QA: Nuriad Islam
Bug Reporting
# SL 09
Issue: Checking 'Sign in with Facebook'
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on Register button at the right corner 3. Click on 'login with Facebook'
Env: Production.
Module: Register
Screenshot: Log in with facebook error
Expected: Should allow user to register
Responsible QA: Nuriad Islam
Bug Reporting
# SL 10
Issue: Checking by selecting ‘Forgot Password’ multiple times
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' multiple times
Env: Production.
Module: Login
Screenrecord: Selecting "Forgot Password" multiple times error
Expected: Account should be temporarily restricted and a message should be displayed
Responsible QA: Nuriad Islam
Bug Reporting
# SL 11
Issue: Verifying inputing old password on 'Set a New Password'
Reproducing Steps:
1. Goto the URL https://www.banglashoppers.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password
Env: Production.
Module: Login
Screenrecord: Inputing Old password on"set a new password" error
Expected: Should not allow user to login and display an error message
Responsible QA: Nuriad Islam

## Test Case Report
Test Case Report | [5 empty] | RESULT
Project Name | Banglashoppers |  |  |  |  | Total No. | Status
Module Name | Account |  |  |  |  | PASS | 40
Feature Name | Register Account & Account Login. |  |  |  |  | FAIL | 11
Test Case Version | 1 |  |  |  |  | NOT EXECUTED | 0
Written By | Nuriad Islam |  |  |  |  | OUT OF SCOPE | 0
Executed By | Nuriad Islam
Reviewed By
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 40 | 11 | 0 | 0 | 51
Grand Total | 40 | 11 | 0 | 0 | 51
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes / No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes / No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes / No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes / No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes / No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes / No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes / No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Mind Maps
Mind Map of BanglaShoppers.Com

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (51/51)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/51)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (40/51)*100 = 78%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (11/51)*100 = 22%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A